Optimal Timeline for Academic Program Development and Approval*

Year I

- By early March Year I

  - Submission of Concept note to the Office of the Provost

- April – early May

  - Preparation of Letter of Intent (LOI) in consultation with Office of the Provost

- By mid-May

  - Approval of LOI by Office of the Provost at Program Concept Review Group (PCRG) Meeting

- Mid-May

  - Submission of LOI to USM

  - Building of new courses can begin (course approval is a separate process from program approval in CIM)

- Mid-June

  - Submission of LOI to MHEC (graduate programs only)

- Jun-Aug

  - If no comments from USM/MHEC, writing of full MHEC proposal

- By Aug 15

  - Submission of final draft of MHEC proposal to Office of the Provost

- By Sept 15

  - Full compliance check of MHEC proposal by Office of the Provost

- By Oct 1

  - Entry of final MHEC proposal into CIM

- By Oct 15

  - Review and approval of program proposal by College Curriculum Committee

- Nov

  - Review and approval of program proposal by University Curriculum Committee (second Monday of the month)

  - Review and approval of program proposal by Graduate Studies Committee (second Friday of the month)

- Dec

  - Review and approval of program proposal by Academic Senate (first Monday of the month)

Year II

- Jan 2

  - Submission of program proposal by Office of the Provost to MHEC and USM

- End Jan

  - USM EPSL committee review of program proposals

- Mid Feb

  - USM approval at the full Board of Regents Meeting

- Early – mid March

  - MHEC approval of proposals submitted on Jan 2

- Spring/Summer

  - Program advertisement and recruitment

- Fall Year II

  - Launch of new program